IT EPMO

# Project Delivery Toolkit Guide

Practical guidance for selecting and using IT EPMO project delivery tools

Version 1.0 | August 2026

Purpose The IT EPMO Project Delivery Toolkit provides practical tools to support projects across the lifecycle. Use the toolkit to add structure where it creates value, while tailoring the level of documentation to the project's size, complexity, risk, methodology, engagement model, and delivery context.

Core principle

Structure, not bureaucracy. The right tool at the right time should make delivery easier, not create work for its own sake.

Internal IT EPMO Guide

## 1. How to Use This Guide

This guide is a practical reference for IT EPMO project managers, project teams, sponsors, and leaders. It explains what each template is for, when to use it, how the templates relate to one another, and how the toolkit should be tailored to the needs of a particular project.

Do not interpret the toolkit as a checklist of 18 mandatory documents. Projects should use the smallest set of tools that provides sufficient clarity, control, accountability, and communication.

### The toolkit is organized around the project lifecycle

| Lifecycle Stage | Primary Purpose | Representative Tools |
| --- | --- | --- |
| Initiate | Understand the request, evaluate the opportunity, and establish the appropriate IT EPMO path. | Project Intake / Engagement Assessment; Project Proposal; Project Charter |
| Plan | Define how the project will be delivered, staffed, governed, communicated, and controlled. | Project Plan; Team Roles; Stakeholder Analysis; Communication Plan; Milestone Plan |
| Deliver & Control | Manage delivery, uncertainty, decisions, changes, and project health. | RAID Log; Risk Register; Decision Log; Change Request; Status Brief |
| Assess & Recover | Evaluate project health and intervene when a project requires focused support. | Project Health Assessment; Project Recovery Plan |
| Close & Learn | Complete operational and administrative closure, capture learning, and document outcomes. | Closure Checklist; Lessons Learned; Project Summary |

### How to decide what to use

Start with the project context: size, complexity, risk, stakeholders, visibility, delivery methodology, and current delivery mode.

Use the IT EPMO Engagement Model to determine the appropriate level of IT EPMO involvement.

Use the Delivery Methodology to determine how the work will be executed: Waterfall, Agile, or Hybrid.

Use the Operating Mode to understand the delivery context: Standard Delivery, Rapid Response, Assessment, or Recovery.

Select only the templates that add value. Reference information maintained elsewhere rather than duplicating it.

## 2. The IT EPMO Framework

The toolkit supports the IT EPMO framework of Engagement Models, Delivery Methodologies, and Operating Modes. These three dimensions describe how much IT EPMO involvement is appropriate, how work will be executed, and the context in which delivery is occurring.

### Engagement Models - how much IT EPMO involvement?

| Engagement Model | Use When |
| --- | --- |
| Autonomous | The team owns delivery with minimal IT EPMO involvement. |
| Guided | The team leads delivery and uses IT EPMO expertise, coaching, standards, or targeted support. |
| Embedded | An IT EPMO resource works directly with the project team in a defined role. |
| Phase Assisted | IT EPMO provides support during defined project phases or activities. |
| Fully Managed | IT EPMO leads project delivery and provides comprehensive project management support. |

### Delivery Methodologies - how will the work be executed?

| Methodology | Use When |
| --- | --- |
| Waterfall | Work is primarily planned sequentially, with defined phases, deliverables, and approvals. |
| Agile | Work is delivered iteratively and incrementally through prioritized backlogs, short delivery cycles, and frequent feedback. |
| Hybrid | Different parts of the project require different delivery approaches and the project intentionally combines them. |

### Operating Modes - what delivery context are we in?

| Operating Mode | Use When |
| --- | --- |
| Standard Delivery Mode | The project is proceeding through the normal delivery lifecycle. |
| Rapid Response Mode | The situation requires urgent, focused action and a lightweight delivery approach. |
| Assessment Mode | IT EPMO is evaluating project health, situation, or delivery needs before determining next steps. |
| Recovery Mode | The project requires structured intervention to stabilize delivery and return to a healthy state. |

## 3. Toolkit Principles

### Tailor to the Project

The appropriate documentation level depends on project complexity, risk, stakeholder impact, leadership visibility, and delivery needs.

### Maintain Information Once

If detailed information is maintained in TDX or another approved system or project artifact, reference the source instead of recreating it elsewhere.

### Use the Simplest Tool That Works

A straightforward project should not require the same documentation burden as a complex enterprise initiative.

### Keep Working Artifacts Current

RAID Logs, Decision Logs, Milestone Plans, Communication Plans, and similar tools only create value when they reflect the current state.

### Separate Governance From Administration

Templates should support decisions, accountability, communication, and delivery, not paperwork for its own sake.

### Use Companion Tools Deliberately

The toolkit is designed as a connected system. Each tool has a distinct purpose; avoid duplicating content across documents.

Tailoring rule Sections marked as applicable or optional may be removed, marked N/A, or referenced through another artifact when they do not add value to the project.

### Use level guide

Required / Core: expected for normally managed projects unless an approved alternative is appropriate. Recommended: use unless there is a clear reason the project does not need the tool. As Needed: use when project circumstances, risk, governance, or delivery mode make the tool valuable. IT EPMO Process Tools are used by IT EPMO to assess or route work and are not necessarily project artifacts.

## 4. Template Catalog

The catalog below is the primary reference for choosing a tool. When in doubt, use the purpose and distinction columns to determine whether an existing artifact already covers the need.

| # | Template | Use Level | When | Primary Use | Audience |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Intake / Engagement Assessment | IT EPMO process tool | At request intake | Captures the request and recommends the Engagement Model, Delivery Methodology, Operating Mode, and next step. | Internal |
| 2 | Project Proposal | As needed | Before authorization | Builds the initial case: need, outcome, high-level scope, timing, resources, cost, and success measures. | Public |
| 3 | Project Charter | Core | Project initiation | Authorizes the project and documents purpose, business need, objectives, scope, sponsors, major deliverables, delivery context, initial risks, and success criteria. | Public |
| 4 | Project Plan | Core | Planning after charter | Defines how the project will be delivered and managed and points to companion artifacts. | Internal |
| 5 | Project Team Roles & Responsibilities | Recommended | Early planning | Establishes the project team, responsibilities, resource commitments, and optional RACI relationships. | Internal |
| 6 | Stakeholder Analysis | Recommended | Planning / discovery | Assesses stakeholder impact, influence, support, interests, concerns, engagement strategy, and ownership. | Internal |
| 7 | Project Communication Plan | Recommended | Planning and delivery | Defines significant or recurring communications, including audience, purpose, message, method, cadence, owner, and feedback. | Public |
| 8 | Project Milestone Plan | Recommended | Planning and delivery | Tracks major deliverables and commitments without recreating the detailed project schedule. | Internal |

## 5. Template Catalog - Continued

| # | Template | Use Level | When | Primary Use | Audience |
| --- | --- | --- | --- | --- | --- |
| 9 | RAID Log | Recommended | Delivery and control | Primary working log for Risks, Assumptions, Issues, and Dependencies. | Internal |
| 10 | Risk Register | As needed | Deeper risk analysis | Advanced risk management: probability, impact, rating, mitigation, contingency, triggers, residual risk, ownership, and escalation. | Internal |
| 11 | Decision Log | Recommended | Throughout delivery | Records material decisions, rationale, decision maker, impact, and follow-up. | Internal |
| 12 | Project Change Request | As needed | Material change proposed | Documents requested changes and the approval decision. | Public |
| 13 | Project Status Brief | As needed | Outside TDX | Provides a concise project-health snapshot for sponsors, leadership, or other audiences outside the official status system. | Internal |
| 14 | Project Health Assessment | As needed | Assessment Mode / concern | Point-in-time assessment of project health with recommended action. | Internal |
| 15 | Project Recovery Plan | As needed | Recovery Mode | Defines stabilization, corrective actions, recovery milestones, governance, leadership decisions, success measures, and exit criteria. | Internal |
| 16 | Project Closure Checklist | Core | Project closeout | Verifies deliverable acceptance, operational transition, documentation, knowledge transfer, outstanding items, and closure activities. | Internal |
| 17 | Lessons Learned | Recommended | Closeout / retrospective | Captures what worked, what could improve, and recommendations for future projects. | Public |
| 18 | Project Summary | Core | Project closeout | Creates the concise final record of project outcomes, accomplishments, significant factors, and follow-up. | Internal |

## 6. Which Tool Should I Use?

Several tools cover related topics. The following distinctions are intended to eliminate unnecessary duplication and help PMs choose the right tool quickly.

| Tool | Core Question |
| --- | --- |
| Project Proposal | Should we pursue this? |
| Project Charter | What are we authorizing? |
| Project Plan | How will we deliver and manage it? |
| Stakeholder Analysis | Who matters and how should we engage them? |
| Communication Plan | What will we communicate, how, when, and by whom? |
| RAID Log | What risks, assumptions, issues, and dependencies are we managing? |
| Risk Register | Which risks need deeper analysis and response planning? |
| Health Assessment | What is the project condition and what action is warranted? |
| Recovery Plan | How will we stabilize and recover the project? |
| Closure Checklist | Did we properly close the project? |
| Lessons Learned | What did we learn? |
| Project Summary | What did we accomplish? |

## 7. Tailoring by Engagement Model

Engagement Models describe the level of IT EPMO involvement. The template set should scale with the level of support, without assuming every project needs every artifact.

| Template | Autonomous | Guided | Embedded | Phase Assisted | Fully Managed | Rapid Response Team |
| --- | --- | --- | --- | --- | --- | --- |
| Project Charter | Core | Core | Core | Core | Core | Core |
| Project Plan | As needed | Recommended | Core | As needed | Core | As needed |
| Team Roles & Responsibilities | As needed | Recommended | Recommended | Recommended | Core | As needed |
| Stakeholder Analysis | As needed | As needed | Recommended | As needed | Recommended | As needed |
| Communication Plan | As needed | Recommended | Recommended | Recommended | Core | As needed |
| Milestone Plan | Recommended | Recommended | Core | Recommended | Core | As needed |
| RAID Log | Recommended | Recommended | Core | Recommended | Core | As needed |
| Decision Log | As needed | Recommended | Recommended | Recommended | Core | As needed |
| Risk Register | As needed | As needed | As needed | As needed | As needed | As needed |
| Status Brief | As needed | As needed | Recommended | As needed | Recommended | As needed |
| Health Assessment | As needed | As needed | As needed | As needed | As needed | As needed |
| Recovery Plan | As needed | As needed | As needed | As needed | As needed | As needed |
| Closure Checklist | Core | Core | Core | Core | Core | Core |
| Lessons Learned | Recommended | Recommended | Recommended | Recommended | Core | Recommended |
| Project Summary | Core | Core | Core | Core | Core | Core |

Guidance The table is intended as a starting point, not a mandate. Project circumstances can justify adding or removing artifacts.

## 8. Tailoring by Operating Mode

| Operating Mode | Primary Focus | Highest-Value Tools |
| --- | --- | --- |
| Standard Delivery Mode | Normal delivery lifecycle and controls. | Project Plan; Milestone Plan; RAID Log; Decision Log; Status reporting; normal closure tools. |
| Rapid Response Mode | Urgent action with minimal bureaucracy. | Intake/assessment; focused RAID/actions; Decision Log; targeted communications; rapid exit criteria. |
| Assessment Mode | Understand the situation and determine what support is needed. | Project Health Assessment; existing project artifacts; stakeholder input; recommendations. |
| Recovery Mode | Stabilize delivery and return the project to a healthy path. | Health Assessment; Recovery Plan; RAID; Milestone Plan; Decision Log; leadership/status communication. |

## 9. TDX and Other Systems of Record

Official status reporting Project managers are responsible for updating official project status in TDX twice monthly. The Project Status Brief is a supplemental communication tool for audiences outside the system.

### Avoiding duplicate information

Use TDX for institutional project status and other required project-system information.

Use the Project Plan to describe how the project will be managed, not to recreate every task or status record.

Use the Milestone Plan for major commitments; keep the detailed schedule in the approved scheduling or work-management system.

Use the RAID Log and Decision Log as active working artifacts, not as narrative appendices to the Project Plan.

Where a companion artifact is the detailed source, reference its location from the Project Plan Artifact Register.

## 10. Public vs. Internal Toolkit

Not every IT EPMO tool should be offered as a self-service public download. Public resources should be useful to stakeholders who may initiate, participate in, or support project work. Internal tools provide deeper project-management and IT EPMO governance capabilities.

### Public website templates

| # | Template | Why It Is Public |
| --- | --- | --- |
| 1 | Project Proposal | Helps stakeholders develop and communicate an initial project opportunity or need. |
| 2 | Project Charter | Shared authorization and alignment artifact for project sponsors and teams. |
| 3 | Project Change Request | Provides a clear mechanism for documenting and evaluating significant project changes. |
| 4 | Project Communication Plan | Supports stakeholder communication planning and can be used collaboratively with project teams. |
| 5 | Lessons Learned | Encourages reflection and organizational learning. |

### Internal IT EPMO-managed templates

Project Intake / Engagement Assessment

Project Plan

Project Team Roles & Responsibilities

Stakeholder Analysis

RAID Log

Risk Register

Decision Log

Project Milestone Plan

Project Status Brief

Project Health Assessment

Project Recovery Plan

Project Closure Checklist

Project Summary

Internal does not mean confidential Internal tools may be shared with sponsors, project teams, stakeholders, or leadership when appropriate. They are simply not offered as general self-service downloads on the public IT EPMO website.

## 11. Template Governance

The IT EPMO owns the toolkit as a managed product. Individual templates should have clear ownership, versioning, and review expectations so that outdated documents do not remain in circulation.

| Governance Element | Standard |
| --- | --- |
| Template Owner | IT EPMO unless another owner is explicitly designated. |
| Versioning | Published templates use a simple Version x.y convention. Internal controlled copies retain Revision History. |
| Review Cycle | Review at least annually and sooner when delivery practices, systems, policy, or IT EPMO standards materially change. |
| Public/Internal Designation | Each template should have a documented audience designation. |
| Retirement | Superseded templates should be removed from active locations and marked retired to prevent accidental reuse. |
| System Consistency | Templates should use the same IT EPMO visual language, terminology, and framework names. |

### Document control for each template

| Control Field | Example |
| --- | --- |
| Template Name | IT EPMO Project Charter |
| Version | 1.0 |
| Owner | IT EPMO |
| Audience | Public / Internal |
| Status | Active |
| Last Reviewed | 08/14/2026 |
| Next Review | 08/2027 |
| Replaces | Prior charter templates, if applicable |

## 12. Quick Reference - Start Here

| If you are... | Start with... |
| --- | --- |
| A stakeholder with a new project idea | Project Proposal, then Project Charter if the initiative proceeds. |
| Requesting IT EPMO help | IT EPMO Intake / Engagement Assessment process. |
| Starting an approved project | Project Charter and Project Plan. |
| Building the project team | Project Team Roles & Responsibilities. |
| Planning stakeholder engagement | Stakeholder Analysis, then Communication Plan. |
| Tracking project control items | RAID Log; add Risk Register when deeper risk analysis is needed. |
| Recording a material project decision | Decision Log. |
| Requesting a significant project change | Project Change Request. |
| Communicating project health outside TDX | Project Status Brief. |
| Concerned about project health | Project Health Assessment. |
| Working to recover a troubled project | Project Recovery Plan. |
| Preparing to close a project | Project Closure Checklist, Lessons Learned, and Project Summary. |

### The IT EPMO promise

Use structure where it adds value. The toolkit is designed to help teams succeed by providing clarity, practical project-management expertise, and consistent delivery practices without unnecessary bureaucracy.

## Appendix A. Revision History

| Version | Date | Owner | Description of Change |
| --- | --- | --- | --- |
| 1.0 | 08/14/2026 | IT EPMO | Initial approved release of the IT EPMO Project Delivery Toolkit Guide. |